## Study Plan
Kick-Off Date | 2023-10-02
Initial Black Hole | 2023-12-18
Daily Working Hours | 6
Weekly Working Days | 4
Weekly Working Hours | 24
Error Margin | 10%
[7 empty] | 22 months |  | 42Evaluators
30% over intra expectations
|  | Intra expected time(H) | Personal Expected time | # Working Days | Starting Date | Expected Finish Date | # Months | Real Finish Date | Gained BH Days | Expected BH Date after
Rank 0 | libft | 70 | 77 | 12.8333 | 2023-10-02 | 2023-10-24 11:00 | 0.74861 | 2023-10-31 | 65 | 2024-02-21
Rank 1 | ft_printf | 70 | 77 | 12.8333 | 2023-11-02 | 2023-11-24 11:00 | 2.0583 |  |  | TBCalculated
| get_next_line | 70 | 77 | 12.8333 | 2023-11-26 11:00 | 2023-12-18 22:00 |  |  |  | TBCalculated
| born2beroot | 40 | 44 | 7.3333 | 2023-12-20 22:00 | 2024-01-02 18:00 |  |  |  | TBCalculated
Rank 2 | push_swap | 60 | 66 | 11 | 2024-01-04 18:00 | 2024-01-24 | 1.9514 |  |  | TBCalculated
| minitalk / pipex | 50 | 55 | 9.1667 | 2024-01-26 | 2024-02-11 01:00 |  |  |  | TBCalculated
| so long / FdF / fract-ol | 60 | 66 | 11 | 2024-02-13 01:00 | 2024-03-03 07:00 |  |  |  | TBCalculated
Rank 3 | philosophers | 70 | 77 | 12.8333 | 2024-03-05 07:00 | 2024-03-27 18:00 | 3.0611 |  |  | TBCalculated
| minishell | 210 | 231 | 38.5 | 2024-03-29 18:00 | 2024-06-05 03:00 |  |  |  | TBCalculated
Rank 4 | NetPractice | 50 | 55 | 9.1667 | 2024-06-07 03:00 | 2024-06-23 04:00 | 4.1117 |  |  | TBCalculated
| cub3d / MiniRT | 280 | 308 | 51.3333 | 2024-06-25 04:00 | 2024-09-23 |  |  |  | TBCalculated
| CPP [00--04] | 42 | 46.2 | 7.7 | 2024-09-25 | 2024-10-08 11:24 |  |  |  | TBCalculated
Rank 5 | CPP [05 - 09] | 140 | 154 | 25.6667 | 2024-10-10 11:24 | 2024-11-24 09:24 | 6.0153 |  |  | TBCalculated
| Inception | 210 | 231 | 38.5 | 2024-11-26 09:24 | 2025-02-01 18:24 |  |  |  | TBCalculated
| webserv / ft_irc | 200 | 220 | 36.6667 | 2025-02-03 18:24 | 2025-04-08 22:24 |  |  |  | TBCalculated
Rank 6 | ft_transcendence | 245 | 269.5 | 44.9167 | 2025-04-10 22:24 | 2025-06-28 12:54 | 2.6201 |  |  | TBCalculated
Formulas:
Starting Date = IF([Real Finish Date, row above]>0,[Real Finish Date, row above],[Expected Finish Date, row above])+2
Expected Finish Date = [Starting Date]+E11*7/B5
Expected BH Date after = IF([Gained BH Days]>0,B3+[Gained BH Days])