## Study Plan
Kick-Off Date | 2023-10-02
Initial Black Hole | 2023-12-18
Daily Working Hours | 6
Weekly Working Days | 5
Weekly Working Hours | 30
Error Margin | 10%
[7 empty] | 17 months |  | 42Evaluators
30% over intra expectations
|  | Intra expected time(H) | Personal Expected time | # Working Days | Starting Date | Expected Finish Date | # Months | Real Finish Date | Gained BH Days | Expected BH Date after
Rank 0 | libft | 70 | 77 | 12.8333 | 2023-10-02 | 2023-10-19 23:12 | 0.59889 |  |  | 0
Rank 1 | ft_printf | 70 | 77 | 12.8333 | 2023-10-21 23:12 | 2023-11-08 22:24 | 1.6733 |  |  | TBCalculated
| get_next_line | 70 | 77 | 12.8333 | 2023-11-10 22:24 | 2023-11-28 21:36 |  |  |  | TBCalculated
| born2beroot | 40 | 44 | 7.3333 | 2023-11-30 21:36 | 2023-12-11 04:00 |  |  |  | TBCalculated
Rank 2 | push_swap | 60 | 66 | 11 | 2023-12-13 04:00 | 2023-12-28 13:36 | 1.5878 |  |  | TBCalculated
| minitalk / pipex | 50 | 55 | 9.1667 | 2023-12-30 13:36 | 2024-01-12 09:36 |  |  |  | TBCalculated
| so long / FdF / fract-ol | 60 | 66 | 11 | 2024-01-14 09:36 | 2024-01-29 19:12 |  |  |  | TBCalculated
Rank 3 | philosophers | 70 | 77 | 12.8333 | 2024-01-31 19:12 | 2024-02-18 18:24 | 2.4622 |  |  | TBCalculated
| minishell | 210 | 231 | 38.5 | 2024-02-20 18:24 | 2024-04-14 16:00 |  |  |  | TBCalculated
Rank 4 | NetPractice | 50 | 55 | 9.1667 | 2024-04-16 16:00 | 2024-04-29 12:00 | 3.316 |  |  | TBCalculated
| cub3d / MiniRT | 280 | 308 | 51.3333 | 2024-05-01 12:00 | 2024-07-12 08:48 |  |  |  | TBCalculated
| CPP [00--04] | 42 | 46.2 | 7.7 | 2024-07-14 08:48 | 2024-07-25 03:31 |  |  |  | TBCalculated
Rank 5 | CPP [05 - 09] | 140 | 154 | 25.6667 | 2024-07-27 03:31 | 2024-09-01 01:55 | 4.8389 |  |  | TBCalculated
| Inception | 210 | 231 | 38.5 | 2024-09-03 01:55 | 2024-10-26 23:31 |  |  |  | TBCalculated
| webserv / ft_irc | 200 | 220 | 36.6667 | 2024-10-28 23:31 | 2024-12-19 07:31 |  |  |  | TBCalculated
Rank 6 | ft_transcendence | 245 | 269.5 | 44.9167 | 2024-12-21 07:31 | 2025-02-22 04:43 | 2.0961 |  |  | TBCalculated
Formulas:
Starting Date = IF([Real Finish Date, row above]>0,[Real Finish Date, row above],[Expected Finish Date, row above])+2
Expected Finish Date = [Starting Date]+E11*7/B5
Expected BH Date after = IF([Gained BH Days]>0,B3+[Gained BH Days])